## Project Tasks
Task ID | Task Name | Task Type | Parent Task ID | WBS Code | Duration (Days) | Start Date | End Date | Actual Start | Actual End | % Complete | Task Agility | Dependencies | Dependency Type | Lag/Lead | Criticality Level | Resource Assignment | Resource Load % | Cost Budget | Actual Cost | Status | Milestone | Deliverables | Blocking Tasks | Blocked By | Notes | Impact Score | Risk Score | Health Indicator | Priority Score | Total Float | Free Float | Critical Path | Weighted Progress | Rolled Up Progress | Variance Days | SPI | CPI | Risk Mitigation | Lessons Learned
P001 | Digital Transformation Initiative | Parent |  | 1 | 120 | 2024-01-01 | 2024-06-17 | 2024-01-01 |  | 35% | Sequential |  |  | 0 | Critical | Program Management | 100% | 5000000 | 1750000 | In Progress | No | Complete digital transformation |  |  | Strategic initiative for 2024 | 70 | 30 | Yellow | 54 | 0 | 0 | Yes | 35 | 35 | 0 | 0.8 | 1
P002 | Phase 1: Discovery & Planning | Parent | P001 | 1.1 | 20 | 2024-01-01 | 2024-01-29 | 2024-01-01 | 2024-01-20 | 100% | Sequential |  |  | 0 | High | PM Team | 100% | 500000 | 485000 | Complete | No | Requirements and architecture | P003,P004 |  | Foundation phase completed successfully | 77 | 0 | Green | 46 | 5 | 5 | No | 100 | 100 | 0 | 1 | 0.9 |  | In progress
C001 | Stakeholder Interviews | Child | P002 | 1.1.1 | 5 | 2024-01-02 | 2024-01-09 | 2024-01-02 | 2024-01-06 | 100% | Parallel |  |  | 0 | High | BA Team | 80% | 50000 | 48000 | Complete | No | Interview notes and findings | C003 |  | Excellent insights gathered | 43 | 0 | Green | 25 | 5 | 5 | No | 100 | 100 | 0 | 1 | 0.9 |  | In progress
C002 | Current State Analysis | Child | P002 | 1.1.2 | 5 | 2024-01-02 | 2024-01-09 | 2024-01-02 | 2024-01-06 | 100% | Parallel |  |  | 0 | High | Tech Architects | 100% | 75000 | 72000 | Complete | No | As-is documentation | C003 |  | Technical debt identified | 43 | 0 | Green | 25 | 5 | 5 | No | 100 | 100 | 0 | 1 | 0.9 |  | In progress
C003 | Future State Design | Child | P002 | 1.1.3 | 7 | 2024-01-07 | 2024-01-17 | 2024-01-07 | 2024-01-13 | 100% | Sequential | C001,C002 | FS | 0 | Critical | Solution Architects | 100% | 100000 | 98000 | Complete | No | To-be architecture | C004 | C001,C002 | Microservices architecture approved | 86 | 0 | Green | 51 | 0 | 0 | Yes | 100 | 100 | 0 | 1 | 0.9 |  | In progress
P003 | Phase 2: Infrastructure Setup | Parent | P001 | 1.2 | 30 | 2024-01-21 | 2024-03-04 | 2024-01-21 |  | 65% | Parallel | P002 | FS | 0 | High | Infrastructure Team | 100% | 1500000 | 975000 | In Progress | No | Cloud infrastructure ready | P004 | P002 | AWS multi-region setup | 66 | 12 | Yellow | 44 | 5 | 5 | No | 65 | 65 | 0 | 1 | 0.9
C005 | Cloud Account Setup | Child | P003 | 1.2.1 | 3 | 2024-01-21 | 2024-01-25 | 2024-01-21 | 2024-01-23 | 100% | Sequential | P002 | FS | 0 | High | Cloud Team | 50% | 10000 | 9500 | Complete | No | AWS accounts ready | C006,C007 |  | Multi-account strategy implemented | 65 | 0 | Green | 39 | 5 | 5 | No | 100 | 100 | 0 | 1 | 0.9 |  | In progress
C007 | Security Framework | Child | P003 | 1.2.3 | 10 | 2024-01-24 | 2024-02-07 | 2024-01-24 |  | 70% | Parallel | C005 | FS | 0 | Critical | Security Team | 100% | 200000 | 140000 | In Progress | No | Security policies & tools |  | C005 | GDPR compliance in progress | 38 | 15 | Yellow | 28 | 0 | 0 | Yes | 70 | 70 | 0 | 1 | 0.9
P004 | Phase 3: Development Sprint 1 | Parent | P001 | 1.3 | 40 | 2024-02-20 | 2024-04-16 |  |  | 0% | Parallel | P003 | SS | 10 | Critical | Dev Team Alpha | 100% | 1000000 | 0 | Planning | No | Core modules developed | P005 | P003 | Agile development approach | 78 | 0 | Green | 46 | 0 | 0 | Yes | 0 | 0 | 0 | 0.8 | 1
M001 | Project Kickoff Complete | Milestone | P002 | 1.1.0 | 0 | 2024-01-01 |  | 2024-01-01 | 2024-01-01 | 100% | Sequential |  |  | 0 | High | All Teams | 0% | 0 | 0 | Complete | Yes | Kickoff meeting held |  |  | Successful project launch | 45 | 0 | Green | 27 | 5 | 5 | No | 100 | 100 | 0 | 1 | 1 |  | In progress
M002 | Infrastructure Ready | Milestone | P003 | 1.2.0 | 0 | 2024-02-19 |  |  |  | 0% | Sequential | C007 | FS | 0 | Critical | Infrastructure Team | 0% | 0 | 0 | Not Started | Yes | Infrastructure sign-off | P004 |  | Gate 2 milestone | 82 | 0 | Green | 49 | 0 | 0 | Yes | 0 | 0 | 0 | 0.8 | 1
R001 | Security Vulnerability Assessment | Child | P003 | 1.2.9 | 3 | 2024-02-01 | 2024-02-06 | 2024-02-01 |  | 40% | Parallel | C007 | SS | 3 | Critical | Security Team | 100% | 30000 | 12000 | Delayed | No | Vulnerability report |  |  | Critical vulnerabilities found - remediation in progress | 44 | 30 | Orange | 38 | 0 | 0 | Yes | 40 | 40 | -2 | 0.8 | 1

## Dashboard
PROJECT DASHBOARD
Total Tasks: | 12
Completed: | 6
At Risk: | 0
Total Budget: | $8,465,000
Actual Cost: | $3,589,500
Budget Used: | 42.4%
STATUS SUMMARY
In Progress | 3
Complete | 6
Planning | 1
Not Started | 1
Delayed | 1

## Instructions
WORKING PROJECT MANAGEMENT TEMPLATE
OVERVIEW | This template provides a comprehensive project tracking system with calculated impact and risk scores.
KEY FEATURES:
Impact Score | Automatically calculated based on duration, dependencies, criticality, and other factors
Risk Score | Dynamic assessment based on status, progress, and health indicators
Health Indicator | Visual status using color coding (Green/Yellow/Orange/Red)
Priority Score | Combined impact and risk for prioritization
USING THE TEMPLATE:
1. Data Entry | Enter your project tasks with parent-child relationships
2. Update Progress | Regularly update % Complete and Status fields
3. Monitor Health | Watch the Health Indicator and Risk Score columns
4. Review Dashboard | Check the Dashboard sheet for KPIs
FORMULAS:
Impact Score | Considers duration, dependencies, criticality, blocking tasks, and budget
Risk Score | Based on status, progress delays, and health indicators
Priority | Impact × 0.6 + Risk × 0.4
BEST PRACTICES:
Daily Updates | Update task status and progress daily
Risk Review | Address high-risk items immediately
Dependencies | Keep dependency information current
Resource Load | Monitor resource utilization levels

## Project Pulse
PROJECT PULSE - HEALTH INDICATORS
Metric | Score | Status | Trend | Target | Gap
Overall Project Health | 87 | Green | ↑ +5% | 85 | -2
Schedule Performance | 93 | Green | ↓ -2% | 90 | -3
Budget Performance | 94 | Green | → 0% | 90 | -4
Risk Management | 100 | Green | ↑ +3% | 80 | -20
Team Utilization | 78 | Yellow | ↑ +5% | 75 | -3
CRITICAL ALERTS
Type | Issue | Severity | Action Required
DELAY | 1 tasks delayed | Orange | Schedule at risk
RESOURCE | 8 resources overloaded | Yellow | Capacity planning needed

## Impact Matrix
IMPACT vs RISK MATRIX
Critical Focus
Task ID | Task Name | Impact | Risk | Priority | Owner | Status
Quick Wins
Task ID | Task Name | Impact | Risk | Priority | Owner | Status
P001 | Digital Transformation Initiat | 70 | 30 | 54 | Program Managem | In Progress
C003 | Future State Design | 86 | 0 | 51 | Solution Archit | Complete
M002 | Infrastructure Ready | 82 | 0 | 49 | Infrastructure | Not Started
P002 | Phase 1: Discovery & Planning | 77 | 0 | 46 | PM Team | Complete
P004 | Phase 3: Development Sprint 1 | 78 | 0 | 46 | Dev Team Alpha | Planning
Risk Mitigation
Task ID | Task Name | Impact | Risk | Priority | Owner | Status
Routine
Task ID | Task Name | Impact | Risk | Priority | Owner | Status
R001 | Security Vulnerability Assessm | 44 | 30 | 38 | Security Team | Delayed
C007 | Security Framework | 38 | 15 | 28 | Security Team | In Progress
M001 | Project Kickoff Complete | 45 | 0 | 27 | All Teams | Complete
C001 | Stakeholder Interviews | 43 | 0 | 25 | BA Team | Complete
C002 | Current State Analysis | 43 | 0 | 25 | Tech Architects | Complete

## Resource Orchestra
RESOURCE CAPACITY & ALLOCATION
Resource/Team | Active Tasks | Avg Load % | Critical Tasks | Blocked | Budget Allocated | Budget Used | Health
Program Management | 1 | 100% | 1 | 0 | $5,000,000 | $1,750,000 (35%) | Red
PM Team | 1 | 100% | 0 | 0 | $500,000 | $485,000 (97%) | Red
Tech Architects | 1 | 100% | 0 | 0 | $75,000 | $72,000 (96%) | Red
Solution Architects | 1 | 100% | 1 | 0 | $100,000 | $98,000 (98%) | Red
Security Team | 2 | 100% | 2 | 0 | $230,000 | $152,000 (66%) | Red
Dev Team Alpha | 1 | 100% | 1 | 0 | $1,000,000 | $0 (0%) | Red
BA Team | 1 | 80% | 0 | 0 | $50,000 | $48,000 (96%) | Yellow
Infrastructure Team | 2 | 50% | 1 | 0 | $1,500,000 | $975,000 (65%) | Green
Cloud Team | 1 | 50% | 0 | 0 | $10,000 | $9,500 (95%) | Green
All Teams | 1 | 0% | 0 | 0 | $0 | $0 (0%) | Green
BOTTLENECK ANALYSIS
Resource | Issue | Impact | Recommendation
Program Management | Overloaded | 1 critical tasks affected | Redistribute load
PM Team | Overloaded | 0 critical tasks affected | Redistribute load
Tech Architects | Overloaded | 0 critical tasks affected | Redistribute load
Solution Architects | Overloaded | 1 critical tasks affected | Redistribute load
Security Team | Overloaded | 2 critical tasks affected | Redistribute load

## Timeline Rhythm
TIMELINE & CRITICAL PATH
UPCOMING MILESTONES
Milestone | Target Date | Days Until | Dependencies | Status | Impact if Delayed
Infrastructure Ready | 2024-02-19 | -501 | 1 | Not Started | High - Blocks multiple tasks
CRITICAL PATH TASKS
Task ID | Task Name | Start | End | Progress | Float | Status
P001 | Digital Transformation Initiative | 2024-01-01 | 2024-06-17 | 35% | 0 | In Progress
C003 | Future State Design | 2024-01-07 | 2024-01-17 | 100% | 0 | Complete
C007 | Security Framework | 2024-01-24 | 2024-02-07 | 70% | 0 | In Progress
P004 | Phase 3: Development Sprint 1 | 2024-02-20 | 2024-04-16 | 0% | 0 | Planning
M002 | Infrastructure Ready | 2024-02-19 |  | 0% | 0 | Not Started
R001 | Security Vulnerability Assessment | 2024-02-01 | 2024-02-06 | 40% | 0 | Delayed
PROJECT VELOCITY
Planned Completion | 6
Actual Completion | 6
Tasks Behind Schedule | 1
Average Delay (days) | 2
Projected Completion | Delayed

## Decision Command
DECISIONS & ACTIONS REQUIRED
Type | Urgency | Task | Action Required | Owner | Impact if Delayed | Due
RESOURCE | Medium | Digital Transformation Initiative | Reallocate resources | Project Manager | Resource burnout risk | Next sprint
RESOURCE | Medium | Phase 1: Discovery & Planning | Reallocate resources | Project Manager | Resource burnout risk | Next sprint
RESOURCE | Medium | Current State Analysis | Reallocate resources | Project Manager | Resource burnout risk | Next sprint
RESOURCE | Medium | Future State Design | Reallocate resources | Project Manager | Resource burnout risk | Next sprint
RESOURCE | Medium | Phase 2: Infrastructure Setup | Reallocate resources | Project Manager | Resource burnout risk | Next sprint
RESOURCE | Medium | Security Framework | Reallocate resources | Project Manager | Resource burnout risk | Next sprint
RESOURCE | Medium | Phase 3: Development Sprint 1 | Reallocate resources | Project Manager | Resource burnout risk | Next sprint
RESOURCE | Medium | Security Vulnerability Assessment | Reallocate resources | Project Manager | Resource burnout risk | Next sprint
QUICK ACTIONS SUMMARY
Total Decisions Pending | 8
Critical Actions | 0
Blockers to Remove | 0
Risk Mitigations | 0
Resource Issues | 8

## Predictive Insights
PREDICTIVE ANALYTICS & RECOMMENDATIONS
COMPLETION PREDICTIONS
Metric | Current | Predicted | Confidence | Trend
Project Completion Date | Apr 30, 2024 | May 15, 2024 | 85% | ↓
Final Budget | $8.5M | $9.0M | 94% | ↑
Tasks at Risk | 0 | 3 | 75% | ↑
Resource Capacity | 78% | 85% | 80% | ↑
EMERGING RISKS
Risk | Probability | Impact | Timeline | Recommended Action
Security Framework Delay | 65% | High | Next 2 weeks | Add security resources immediately
Resource Burnout | 45% | Medium | Next month | Implement resource rotation plan
Budget Overrun | 30% | Medium | Q2 2024 | Review and optimize spending
OPTIMIZATION OPPORTUNITIES
Opportunity | Action | Expected Benefit | Confidence
Resource Reallocation | Move 2 developers from Phase 2 to Phase 3 | 15% faster delivery | High
Parallel Execution | Run testing in parallel with development | 10 days saved | Medium
Scope Adjustment | Defer 2 non-critical features to Phase 2 | 20% risk reduction | Medium
Tool Automation | Implement automated testing for APIs | 30% effort reduction | High