## Project Tasks
Task ID | Task Name | Task Type | Parent Task ID | Duration (Days) | Start Date | End Date | Actual Start | Actual End | % Complete | Task Agility | Dependencies | Dependency Type | Impact Score | Criticality Level | Resource Assignment | Status | Health Indicator | Notes | Blocking Tasks | Blocked By | Total Float | Free Float | Weighted Progress | Rolled Up Progress
P001 | Project Initiation | Parent |  | 10 | 2024-01-01 | 45303 |  |  | 0 | Sequential |  |  | 51 | High | PM Team | In Progress | Red | Project kickoff phase |  |  |  |  | 28.2258 | 28.2258
P002 | Requirements Gathering | Parent |  | 15 | 2024-01-11 | 45322 |  |  | 0 | Sequential | P001 | FS | 52 | High | Business Analysts | Not Started | Red | Gather all requirements |  |  |  |  | 26.087 | 26.087
P003 | Design Phase | Parent |  | 20 | 2024-01-26 | 45344 |  |  | 100 | Parallel | P002 | FS | 37 | High | Design Team | Complete | Green | System design |  |  |  |  | #DIV/0! | #DIV/0!
P004 | Development | Parent |  | 40 | 2024-02-15 | 45392 |  |  | 100 | Parallel | P003 | FS | 45 | High | Dev Team | Complete | Green | Build the system |  |  |  |  | #DIV/0! | #DIV/0!
P005 | Testing | Parent |  | 15 | 2024-03-26 | 45397 |  |  | 0 | Sequential | P004 | FS | 47 | High | QA Team | Not Started | Red | System testing |  |  |  |  | #DIV/0! | #DIV/0!
C001 | Form Project Team | Child | P001 | 3 | 2024-01-01 | 45294 |  |  | 0 | Sequential |  | SS | 37 | High | HR | Not Started | Red | Assemble team |  |  |  |  | 0 | 0
C002 | Define Project Charter | Child | P001 | 2 | 2024-01-04 | 45296 |  |  | 100 | Sequential | C001 | FS | 35 | High | PM | Complete | Green | Create charter |  |  |  |  | 100 | 100
C003 | Stakeholder Analysis | Child | P001 | 2 | 2024-01-06 | 45299 |  |  | 0 | Parallel | C001 | FS | 18 | Medium | PM | Not Started | Red | Identify stakeholders |  |  |  |  | 0 | 0
C004 | Kickoff Meeting | Child | P001 | 1 | 2024-01-08 | 45299 |  |  | 0 | Sequential | C002,C003 | FS | 34 | High | All | Not Started | Red | Project kickoff |  |  |  |  | 0 | 0
C005 | Business Requirements | Child | P002 | 5 | 2024-01-11 | 45308 |  |  | 0 | Sequential | P001 | FS | 31 | High | BA | Not Started | Red | Gather business reqs |  |  |  |  | 0 | 0
C006 | Technical Requirements | Child | P002 | 5 | 2024-01-16 | 45313 |  |  | 0 | Sequential | C005 | FS | 30 | High | Tech Lead | Not Started | Red | Define tech reqs |  |  |  |  | 0 | 0
C007 | Requirements Review | Child | P002 | 3 | 2024-01-21 | 45314 |  |  | 100 | Sequential | C005,C006 | FS | 30 | High | All | Complete | Green | Review all reqs |  |  |  |  | 100 | 100
C008 | Requirements Sign-off | Child | P002 | 2 | 2024-01-24 | 45316 |  |  | 0 | Sequential | C007 | FS | 24 | High | Stakeholders | Not Started | Red | Get approval |  |  |  |  | 0 | 0
[9 empty] | 0 |  |  |  | 7 |  |  |  | Green | [5 empty] | 0 | 0
[9 empty] | 0 |  |  |  | 5 |  |  |  | Green | [5 empty] | 0 | 0
[9 empty] | 0 |  |  |  | 4 |  |  |  | Green | [5 empty] | 0 | 0
[9 empty] | 0 |  |  |  | 2 |  |  |  | Green | [5 empty] | 0 | 0
[9 empty] | 0 |  |  |  | 0 |  |  |  | Green | [5 empty] | 0 | 0
Formulas:
End Date = IF(AND([Start Date]<>"",[Duration (Days)]<>""),WORKDAY([Start Date],[Duration (Days)]-1),"")
Health Indicator = IF([Status]="Complete","Green", IF(OR([Status]="Delayed",[Status]="Blocked"),"Red", IF(AND(J2<100,[End Date]<TODAY()),"Red", IF(AND(J2<80,[End Date]<=TODAY()+7),"Yellow","Green"))))

## Dashboard
PROJECT EXECUTIVE DASHBOARD
KEY METRICS
Overall Progress: |  | #DIV/0!
Critical Tasks: |  | 12
Delayed Tasks: |  | 0
Blocked Tasks: |  | 0
Average Impact Score: |  | 27.1667
Health Status: |  | 9 Red, 0 Yellow, 9 Green
TOP 5 CRITICAL TASKS BY IMPACT
Task Name | Impact Score | Status | Health

## Instructions
PROJECT MANAGEMENT TEMPLATE - USER GUIDE
OVERVIEW: | This template uses an impact-based scoring system to provide accurate project progress tracking.
KEY FEATURES:
1. Impact Score Algorithm: | Calculates task importance based on duration, dependencies, criticality, and timeline position
2. Parent-Child Hierarchy: | Progress rolls up from child tasks to parent tasks weighted by impact scores
3. Automatic Health Tracking: | Health indicators update based on progress and deadlines
HOW TO USE:
1. Enter Tasks: | Start by entering parent tasks, then add child tasks with parent IDs
2. Set Dependencies: | Link tasks using Task IDs in the Dependencies column
3. Assign Resources: | Add team members or departments to Resource Assignment
4. Track Progress: | Update Actual Start dates and Status - progress calculates automatically
5. Monitor Health: | Watch the Health Indicator column for risk identification
IMPACT SCORE COMPONENTS:
- Duration Weight (25%): | Longer tasks have higher impact
- Dependency Count (30%): | More dependencies increase impact
- Resource Criticality (20%): | High criticality resources increase impact
- Timeline Position (25%): | Earlier tasks have higher impact
BEST PRACTICES:
1. Update Daily: | Keep actual dates and status current for accurate tracking
2. Review Impact Scores: | Focus on high-impact tasks for maximum efficiency
3. Use Filters: | Filter by Status, Health, or Resource for focused views
4. Check Dashboard: | Review executive dashboard for quick project health assessment