## Project Tasks
Task ID | Task Name | Task Type | Parent Task ID | Duration (Days) | Start Date | End Date | Actual Start | Actual End | % Complete | Task Agility | Dependencies | Dependency Type | Impact Score | Criticality Level | Resource Assignment | Status | Health Indicator | Notes | Blocking Tasks | Blocked By | Total Float | Free Float | Weighted Progress | Rolled Up Progress
P001 | Project Initiation | Parent |  | 10 | 2024-01-01 |  |  |  |  | Sequential |  |  |  | High | PM Team | Not Started |  | Project kickoff phase
P002 | Requirements Gathering | Parent |  | 15 | 2024-01-11 |  |  |  |  | Sequential | P001 | FS |  | High | Business Analysts | Not Started |  | Gather all requirements
P003 | Design Phase | Parent |  | 20 | 2024-01-26 |  |  |  |  | Parallel | P002 | FS |  | High | Design Team | Not Started |  | System design
P004 | Development | Parent |  | 40 | 2024-02-15 |  |  |  |  | Parallel | P003 | FS |  | High | Dev Team | Not Started |  | Build the system
P005 | Testing | Parent |  | 15 | 2024-03-26 |  |  |  |  | Sequential | P004 | FS |  | High | QA Team | Not Started |  | System testing
C001 | Form Project Team | Child | P001 | 3 | 2024-01-01 |  |  |  |  | Sequential |  |  |  | High | HR | Not Started |  | Assemble team
C002 | Define Project Charter | Child | P001 | 2 | 2024-01-04 |  |  |  |  | Sequential | C001 | FS |  | High | PM | Not Started |  | Create charter
C003 | Stakeholder Analysis | Child | P001 | 2 | 2024-01-06 |  |  |  |  | Parallel | C001 | FS |  | Medium | PM | Not Started |  | Identify stakeholders
C004 | Kickoff Meeting | Child | P001 | 1 | 2024-01-08 |  |  |  |  | Sequential | C002,C003 | FS |  | High | All | Not Started |  | Project kickoff
C005 | Business Requirements | Child | P002 | 5 | 2024-01-11 |  |  |  |  | Sequential | P001 | FS |  | High | BA | Not Started |  | Gather business reqs
C006 | Technical Requirements | Child | P002 | 5 | 2024-01-16 |  |  |  |  | Sequential | C005 | FS |  | High | Tech Lead | Not Started |  | Define tech reqs
C007 | Requirements Review | Child | P002 | 3 | 2024-01-21 |  |  |  |  | Sequential | C005,C006 | FS |  | High | All | Not Started |  | Review all reqs
C008 | Requirements Sign-off | Child | P002 | 2 | 2024-01-24 |  |  |  |  | Sequential | C007 | FS |  | High | Stakeholders | Not Started |  | Get approval
Formulas:
End Date = IF(AND([Start Date]<>"",[Duration (Days)]<>""),WORKDAY([Start Date],[Duration (Days)]-1),"")
Health Indicator = IF([Status]="Complete","Green", IF(OR([Status]="Delayed",[Status]="Blocked"),"Red", IF(AND(J2<100,[End Date]<TODAY()),"Red", IF(AND(J2<80,[End Date]<=TODAY()+7),"Yellow","Green"))))

## Dashboard
PROJECT EXECUTIVE DASHBOARD
KEY METRICS
Overall Progress:
Critical Tasks:
Delayed Tasks:
Blocked Tasks:
Average Impact Score:
Health Status:
TOP 5 CRITICAL TASKS BY IMPACT
Task Name | Impact Score | Status | Health

## Instructions
PROJECT MANAGEMENT TEMPLATE - USER GUIDE
OVERVIEW: | This template uses an impact-based scoring system to provide accurate project progress tracking.
KEY FEATURES:
1. Impact Score Algorithm: | Calculates task importance based on duration, dependencies, criticality, and timeline position
2. Parent-Child Hierarchy: | Progress rolls up from child tasks to parent tasks weighted by impact scores
3. Automatic Health Tracking: | Health indicators update based on progress and deadlines
HOW TO USE:
1. Enter Tasks: | Start by entering parent tasks, then add child tasks with parent IDs
2. Set Dependencies: | Link tasks using Task IDs in the Dependencies column
3. Assign Resources: | Add team members or departments to Resource Assignment
4. Track Progress: | Update Actual Start dates and Status - progress calculates automatically
5. Monitor Health: | Watch the Health Indicator column for risk identification
IMPACT SCORE COMPONENTS:
- Duration Weight (25%): | Longer tasks have higher impact
- Dependency Count (30%): | More dependencies increase impact
- Resource Criticality (20%): | High criticality resources increase impact
- Timeline Position (25%): | Earlier tasks have higher impact
BEST PRACTICES:
1. Update Daily: | Keep actual dates and status current for accurate tracking
2. Review Impact Scores: | Focus on high-impact tasks for maximum efficiency
3. Use Filters: | Filter by Status, Health, or Resource for focused views
4. Check Dashboard: | Review executive dashboard for quick project health assessment