## Project Tasks
Task ID | Task Name | Task Type | Parent Task ID | WBS Code | Duration (Days) | Start Date | End Date | Actual Start | Actual End | % Complete | Task Agility | Dependencies | Dependency Type | Lag/Lead | Impact Score | Risk Score | Criticality Level | Priority Score | Resource Assignment | Resource Load % | Cost Budget | Actual Cost | Status | Health Indicator | Milestone | Deliverables | Blocking Tasks | Blocked By | Total Float | Free Float | Critical Path | Weighted Progress | Rolled Up Progress | Variance Days | SPI | CPI | Risk Mitigation | Lessons Learned | Notes
P001 | Project Phoenix - Digital Transformation | Parent |  | 1 | 120 | 2024-01-01 | 45457 |  |  |  | Sequential |  |  | 0 | #NAME? |  | Critical |  | Program Management | 100 | 5000000 | 0 | In Progress |  | No | Complete digital transformation |  |  | 119 | 119 | No | #NAME? |  |  |  |  | Risk assessment in progress |  | Strategic initiative
P002 | Phase 1: Discovery & Planning | Parent | P001 | 1.1 | 20 | 2024-01-01 | 45317 |  |  | 100 | Sequential |  |  | 0 | #NAME? | 24 | High | #NAME? | PM Team | 100 | 500000 | 0 | Complete | Green | No | Requirements and architecture |  |  | 19 | 19 | No | #NAME? |  |  | 0.05 |  |  | Stakeholder alignment critical | Foundation phase
P003 | Phase 2: Infrastructure Setup | Parent | P001 | 1.2 | 30 | 2024-01-21 | 45351 |  |  |  | Parallel | P002 | FS | 0 | #NAME? |  | High |  | Infrastructure Team | 100 | 1500000 | 0 | In Progress |  | No | Cloud infrastructure ready |  |  | 28 | 28 | No | #NAME? |  |  |  |  | Cloud provider selection |  | Technical foundation
P004 | Phase 3: Development Sprint 1 | Parent | P001 | 1.3 | 40 | 2024-02-20 | 45411 |  |  | 0 | Parallel | P003 | SS+10 | 10 | #NAME? | 30 | Critical | #NAME? | Dev Team Alpha | 100 | 1000000 | 0 | Planning | Orange | No | Core modules developed |  |  | 49 | 49 | No | #NAME? | [6 empty] | Agile development
P005 | Phase 4: Integration & Testing | Parent | P001 | 1.4 | 20 | 2024-04-01 | 45401 |  |  | 0 | Sequential | P004 | FS-5 | -5 | #NAME? | 24 | High | #NAME? | QA Team | 100 | 750000 | 0 | Not Started | Orange | No | System integration complete |  |  | 14 | 14 | No | 0 |  |  |  |  | Test automation required |  | Quality assurance
P006 | Phase 5: Deployment & GoLive | Parent | P001 | 1.5 | 10 | 2024-04-21 | 45414 |  |  | 0 | Sequential | P005 | FS | 0 | #NAME? | 30 | Critical | #NAME? | DevOps Team | 100 | 250000 | 0 | Not Started | Orange | No | System live in production |  |  | 8 | 8 | No | 0 |  |  |  |  | Rollback plan ready |  | Go-live phase
M001 | Project Kickoff Complete | Milestone | P002 | 1.1.0 | 0 | 2024-01-01 | 45289 | 2024-01-01 |  | 100 | Sequential |  |  | 0 | #NAME? | 54 | High | #NAME? | All Teams | 0 | 0 | 0 | Complete | Green | Yes | Kickoff meeting held |  |  | -1 | -1 | Yes | 100 |  |  | 100 |  |  | Great team energy | Key milestone
M002 | Requirements Signed Off | Milestone | P002 | 1.1.99 | 0 | 2024-01-20 | 45310 |  |  | 0 | Sequential | C004 | FS | 0 | #NAME? | 98 | Critical | #NAME? | Stakeholders | 0 | 0 | 0 | Not Started | Red | Yes | Requirements approval |  |  | -1 | -1 | Yes | 0 | [6 empty] | Gate 1
C001 | Stakeholder Interviews | Child | P002 | 1.1.1 | 5 | 2024-01-02 | 45299 | 2024-01-02 |  | 100 | Parallel | M001 | FS | 0 | #NAME? | 24 | High | #NAME? | BA Team | 80 | 50000 | 45000 | Complete | Green | No | Interview notes |  |  | 4 | 4 | No | 100 |  |  | 0.01 | 1.11 |  | Excellent insights gathered | Completed on time
C002 | Current State Analysis | Child | P002 | 1.1.2 | 5 | 2024-01-02 | 45299 | 2024-01-02 |  | 100 | Parallel | M001 | FS | 0 | #NAME? | 24 | High | #NAME? | Tech Architects | 100 | 75000 | 70000 | Complete | Green | No | As-is documentation |  |  | 4 | 4 | No | 100 |  |  | 0.01 | 1.07 |  | Legacy system complexities | Technical debt identified
C003 | Future State Design | Child | P002 | 1.1.3 | 7 | 2024-01-07 | 45306 | 2024-01-08 |  | 100 | Sequential | C001,C002 | FS | 0 | #NAME? | 30 | Critical | #NAME? | Solution Architects | 100 | 100000 | 95000 | Complete | Green | No | To-be architecture |  |  | 5 | 5 | No | 100 |  |  | 0.01 | 1.05 |  | Cloud-native approach | Microservices architecture
C004 | Requirements Documentation | Child | P002 | 1.1.4 | 3 | 2024-01-14 | 45307 | 2024-01-15 |  | 100 | Sequential | C003 | FS | 0 | #NAME? | 42 | High | #NAME? | BA Team | 100 | 25000 | 25000 | Complete | Green | No | BRD & FRD documents | M002 |  | 1 | 1 | No | 100 |  |  | 0 | 1 |  | Clear requirements | Well documented
C005 | Cloud Account Setup | Child | P003 | 1.2.1 | 3 | 2024-01-21 | 45314 | 2024-01-21 |  | 100 | Sequential | P002 | FS | 0 | #NAME? | 42 | High | #NAME? | Cloud Team | 50 | 10000 | 9500 | Complete | Green | No | AWS accounts ready |  |  | 1 | 1 | No | 100 |  |  | 0 | 1.05 |  | Multi-account strategy | Security first approach
C006 | Network Architecture | Child | P003 | 1.2.2 | 5 | 2024-01-24 | 45321 | 2024-01-25 |  | 100 | Sequential | C005 | FS | 0 | #NAME? | 30 | Critical | #NAME? | Network Engineers | 100 | 150000 | 145000 | Complete | Green | No | VPC and connectivity |  |  | 4 | 4 | No | 100 |  |  | 0.01 | 1.03 |  | Zero-trust model | Implemented successfully
C007 | Security Framework | Child | P003 | 1.2.3 | 7 | 2024-01-24 | 45323 | 2024-01-26 |  | 99 | Parallel | C005 | FS | 0 | #NAME? | 30 | Critical | #NAME? | Security Team | 100 | 200000 | 150000 | In Progress | Yellow | No | Security policies & tools |  |  | 6 | 6 | No | 99 |  |  | 0.02 | 1.33 | Additional security review | Compliance requirements | GDPR compliance needed
C008 | CI/CD Pipeline Setup | Child | P003 | 1.2.4 | 10 | 2024-01-29 | 45331 |  |  |  | Sequential | C006 | FS | 0 | #NAME? |  | High |  | DevOps Team | 100 | 100000 | 40000 | In Progress |  | No | Automated pipelines | C009,C010 |  | 9 | 9 | No |  |  |  |  | 2.5 |  | GitOps approach | Jenkins to GitLab migration
C009 | Development Environment | Child | P003 | 1.2.5 | 5 | 2024-02-08 | 45336 |  |  |  | Parallel | C008 | SS | 0 | #NAME? |  | Medium |  | DevOps Team | 80 | 50000 | 5000 | In Progress |  | No | Dev env ready |  | C008 | 4 | 4 | No |  |  |  |  | 10 |  |  | Containerized approach
C010 | Testing Environment | Child | P003 | 1.2.6 | 5 | 2024-02-08 | 45336 |  |  |  | Parallel | C008 | SS | 0 | #NAME? |  | Medium |  | QA Team | 80 | 50000 | 5000 | In Progress |  | No | Test env ready |  | C008 | 4 | 0 | Yes |  |  |  |  | 10 |  |  | Automated provisioning
C011 | User Authentication Module | Child | P004 | 1.3.1 | 10 | 2024-03-01 | 45365 |  |  | 0 | Parallel | C009 | FS | 0 | #NAME? | 30 | Critical | #NAME? | Team Alpha | 100 | 150000 | 0 | Not Started | Orange | No | OAuth2 implementation |  |  | 9 | 9 | No | 0 | [6 empty] | Planning phase
C012 | API Gateway Development | Child | P004 | 1.3.2 | 8 | 2024-03-01 | 45363 |  |  | 0 | Parallel | C009 | FS | 0 | #NAME? | 24 | High | #NAME? | Team Beta | 100 | 120000 | 0 | Not Started | Orange | No | REST API gateway |  |  | 7 | 7 | No | 0 | [6 empty] | GraphQL consideration
C013 | Database Schema Design | Child | P004 | 1.3.3 | 5 | 2024-03-01 | 45358 |  |  | 0 | Sequential | C009 | FS | 0 | #NAME? | 30 | Critical | #NAME? | Data Team | 100 | 80000 | 0 | Not Started | Orange | No | Optimized schema | C014,C015 |  | 4 | 4 | No | 0 | [6 empty] | NoSQL evaluation
C014 | Core Business Logic | Child | P004 | 1.3.4 | 15 | 2024-03-06 | 45377 |  |  | 0 | Sequential | C013 | FS | 0 | #NAME? | 75 | Critical | #NAME? | Team Alpha | 100 | 250000 | 0 | Not Started | Orange | No | Business rules engine |  | C013 | 14 | 0 | Yes | 0 | [6 empty] | Domain-driven design
C015 | Data Migration Scripts | Child | P004 | 1.3.5 | 10 | 2024-03-06 | 45370 |  |  | 0 | Parallel | C013 | FS | 0 | #NAME? | 60 | High | #NAME? | Data Team | 100 | 100000 | 0 | Not Started | Orange | No | ETL processes |  | C013 | 9 | 0 | Yes | 0 | [6 empty] | Data quality critical
R001 | Technical Debt Assessment | Child | P002 | 1.1.5 | 3 | 2024-01-10 | 45303 | 2024-01-11 |  | 100 | Parallel | C002 | SS | 0 | #NAME? | 35 | Medium | #NAME? | Tech Leads | 50 | 20000 | 18000 | Complete | Green | No | Debt register |  |  | 2 | 2 | No | 100 |  |  | 0 | 1.11 | High technical debt found | Refactoring needed | Legacy system issues
R002 | Security Vulnerability Scan | Child | P003 | 1.2.7 | 2 | 2024-02-01 | 45329 |  |  |  | Parallel | C007 | SS+3 | 3 | #NAME? |  | Critical |  | Security Team | 100 | 30000 | 15000 | In Progress |  | No | Vulnerability report |  |  | 4 | 4 | No |  |  |  |  | 2 | Critical vulnerabilities found | Immediate action required | Zero-day patch needed
[10 empty] | 0 |  |  |  |  | #NAME? | 20 |  | #NAME? | [5 empty] | Green | [6 empty] | No | 0
[10 empty] | 0 |  |  |  |  | #NAME? | 20 |  | #NAME? | [5 empty] | Green | [6 empty] | No | 0
[10 empty] | 0 |  |  |  |  | #NAME? | 20 |  | #NAME? | [5 empty] | Green | [6 empty] | No | 0
[10 empty] | 0 |  |  |  |  | #NAME? | 20 |  | #NAME? | [5 empty] | Green | [6 empty] | No | 0
[10 empty] | 0 |  |  |  |  | #NAME? | 20 |  | #NAME? | [5 empty] | Green | [6 empty] | No | 0
[10 empty] | 0 |  |  |  |  | #NAME? | 20 |  | #NAME? | [5 empty] | Green | [6 empty] | No | 0
[10 empty] | 0 |  |  |  |  | #NAME? | 20 |  | #NAME? | [5 empty] | Green | [6 empty] | No | 0
[10 empty] | 0 |  |  |  |  | #NAME? | 20 |  | #NAME? | [5 empty] | Green | [6 empty] | No | 0
[10 empty] | 0 |  |  |  |  | #NAME? | 20 |  | #NAME? | [5 empty] | Green | [6 empty] | No | 0
[10 empty] | 0 |  |  |  |  | #NAME? | 20 |  | #NAME? | [5 empty] | Green | [6 empty] | No | 0
[10 empty] | 0 |  |  |  |  | #NAME? | 20 |  | #NAME? | [5 empty] | Green | [6 empty] | No | 0
[10 empty] | 0 |  |  |  |  | #NAME? | 20 |  | #NAME? | [5 empty] | Green | [6 empty] | No | 0
[10 empty] | 0 |  |  |  |  | #NAME? | 20 |  | #NAME? | [5 empty] | Green | [6 empty] | No | 0
[10 empty] | 0 |  |  |  |  | #NAME? | 20 |  | #NAME? | [5 empty] | Green | [6 empty] | No | 0
[10 empty] | 0 |  |  |  |  | #NAME? | 20 |  | #NAME? | [5 empty] | Green | [6 empty] | No | 0
[10 empty] | 0 |  |  |  |  | #NAME? | 20 |  | #NAME? | [5 empty] | Green | [6 empty] | No | 0
[10 empty] | 0 |  |  |  |  | #NAME? | 20 |  | #NAME? | [5 empty] | Green | [6 empty] | No | 0
[10 empty] | 0 |  |  |  |  | #NAME? | 20 |  | #NAME? | [5 empty] | Green | [6 empty] | No | 0
[10 empty] | 0 |  |  |  |  | #NAME? | 20 |  | #NAME? | [5 empty] | Green | [6 empty] | No | 0
[10 empty] | 0 |  |  |  |  | #NAME? | 20 |  | #NAME? | [5 empty] | Green | [6 empty] | No | 0
[10 empty] | 0 |  |  |  |  | #NAME? | 20 |  | #NAME? | [5 empty] | Green | [6 empty] | No | 0
[10 empty] | 0 |  |  |  |  | #NAME? | 20 |  | #NAME? | [5 empty] | Green | [6 empty] | No | 0
[10 empty] | 0 |  |  |  |  | #NAME? | 20 |  | #NAME? | [5 empty] | Green | [6 empty] | No | 0
Formulas:
End Date = IF(AND([Start Date]<>"",[Duration (Days)]<>""), IF([Lag/Lead]<>"",WORKDAY([Start Date],[Duration (Days)]-1+[Lag/Lead]),WORKDAY([Start Date],[Duration (Days)]-1)),"")
Health Indicator = IF([Status]="Complete","Green", IF([Status]="Cancelled","Black", IF(OR([Status]="Blocked",[Risk Score]>80),"Red", IF(OR([Status]="Delayed",[Risk Score]>60,AND(K2<50,[End Date]<TODAY())),"Orange", IF(OR([Risk Score]>40,AND(K2<80,[End Date]<=TODAY()+7),[SPI]<0.9),"Yellow", "Green")))))
Total Float = IF(AND([End Date]<>"",[Start Date]<>""),NETWORKDAYS(TODAY(),[End Date])-NETWORKDAYS(TODAY(),[Start Date]),"")
SPI = IF(AND(K2>0,[Duration (Days)]<>""),ROUND(K2/MAX((TODAY()-[Start Date])/([End Date]-[Start Date])*100,1),2),"")

## Analytics Dashboard
PROJECT ANALYTICS DASHBOARD
Overall Progress |  | On-Time Delivery |  | At Risk Tasks |  | Critical Issues |  | Budget Health |  | Resource Utilization
#NAME? | [7 empty] | 1696.4% |  | 85.6%
RISK MATRIX | [5 empty] | RESOURCE ANALYSIS
| Very Low | Low | Medium | High | Very High | Resource | Allocated Tasks | Utilization % | Capacity
Minimal | 20 | 40 | 60 | 80 | 100
Minor | 40 | 80 | 120 | 160 | 200
Moderate | 60 | 120 | 180 | 240 | 300
Major | 80 | 160 | 240 | 320 | 400
Severe | 100 | 200 | 300 | 400 | 500

## Gantt Chart
PROJECT GANTT CHART
This sheet provides a visual timeline of all project tasks.
Use conditional formatting to create Gantt bars based on start/end dates.
Task ID | Task Name | Start | End | Duration | Progress
P001 | Project Phoenix - Digital Transformation | 2024-01-01 | 45457 | 120
P002 | Phase 1: Discovery & Planning | 2024-01-01 | 45317 | 20 | 100
P003 | Phase 2: Infrastructure Setup | 2024-01-21 | 45351 | 30
P004 | Phase 3: Development Sprint 1 | 2024-02-20 | 45411 | 40 | 0
P005 | Phase 4: Integration & Testing | 2024-04-01 | 45401 | 20 | 0
P006 | Phase 5: Deployment & GoLive | 2024-04-21 | 45414 | 10 | 0
M001 | Project Kickoff Complete | 2024-01-01 | 45289 | 0 | 100
M002 | Requirements Signed Off | 2024-01-20 | 45310 | 0 | 0
C001 | Stakeholder Interviews | 2024-01-02 | 45299 | 5 | 100
C002 | Current State Analysis | 2024-01-02 | 45299 | 5 | 100
C003 | Future State Design | 2024-01-07 | 45306 | 7 | 100
C004 | Requirements Documentation | 2024-01-14 | 45307 | 3 | 100
C005 | Cloud Account Setup | 2024-01-21 | 45314 | 3 | 100
C006 | Network Architecture | 2024-01-24 | 45321 | 5 | 100
C007 | Security Framework | 2024-01-24 | 45323 | 7 | 99
C008 | CI/CD Pipeline Setup | 2024-01-29 | 45331 | 10
C009 | Development Environment | 2024-02-08 | 45336 | 5
C010 | Testing Environment | 2024-02-08 | 45336 | 5
C011 | User Authentication Module | 2024-03-01 | 45365 | 10 | 0
C012 | API Gateway Development | 2024-03-01 | 45363 | 8 | 0
C013 | Database Schema Design | 2024-03-01 | 45358 | 5 | 0
C014 | Core Business Logic | 2024-03-06 | 45377 | 15 | 0
C015 | Data Migration Scripts | 2024-03-06 | 45370 | 10 | 0
R001 | Technical Debt Assessment | 2024-01-10 | 45303 | 3 | 100
R002 | Security Vulnerability Scan | 2024-02-01 | 45329 | 2
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0
0 | 0 | 0 |  | 0 | 0

## Reports
AUTOMATED PROJECT REPORTS
EXECUTIVE SUMMARY
Project Status:
Overall Progress: | #NAME?
Schedule Performance:
Budget Performance: | Under Budget
Critical Issues:
Next Milestone: | Project Kickoff Complete
CRITICAL PATH ANALYSIS
RISK ASSESSMENT
RESOURCE ALLOCATION
BUDGET ANALYSIS
SCHEDULE VARIANCE

## User Guide
PROJECT MANAGEMENT TEMPLATE v2.0 - COMPREHENSIVE GUIDE
QUICK START
1. Project Setup | Enter project phases as Parent tasks | Use WBS codes for hierarchy
2. Task Entry | Add Child tasks under each Parent | Set dependencies and lag/lead times
3. Resource Assignment | Assign teams and set utilization % | Monitor resource conflicts
4. Progress Tracking | Update Status and Actual dates daily | System auto-calculates progress
5. Risk Management | Review Risk Scores regularly | Document mitigation strategies
ADVANCED FEATURES
Impact Score Algorithm | ML-enhanced calculation | Considers 8+ factors including dependencies, resources, timeline
Risk Assessment | Automatic risk scoring | Based on delays, variances, and performance indices
Critical Path Analysis | Real-time CP calculation | Shows float and highlights critical tasks
Resource Optimization | Load balancing alerts | Prevents resource conflicts
Earned Value Management | SPI and CPI tracking | Budget and schedule performance
FORMULAS EXPLAINED
Impact Score | Weighted calculation | Duration(20%) + Dependencies(25%) + Criticality(15%) + Position(15%) + Resources(10%) + Milestone(10%) + Budget(5%)
Risk Score | Dynamic assessment | Status risks + Schedule variance + Performance indices + Float analysis
Health Indicator | Multi-factor health | Combines progress, risk, schedule, and budget factors
BEST PRACTICES
Daily Updates | Update task status daily | Accurate data ensures reliable predictions
Dependency Management | Define all dependencies upfront | Use appropriate relationship types
Resource Planning | Keep utilization below 85% | Allow buffer for unexpected work
Risk Mitigation | Address high-risk items first | Document mitigation strategies
Communication | Use dashboards for stakeholders | Export reports weekly
TROUBLESHOOTING
Circular References | Check parent-child relationships | Ensure no task is its own parent
Performance Issues | Limit active tasks to 500 | Archive completed projects
Formula Errors | Verify data types | Check for empty required fields
SHORTCUTS & TIPS
Ctrl+Shift+L | Toggle filters | Quick data filtering
Alt+H+O+I | Auto-fit columns | Optimize column widths
F9 | Recalculate | Force formula updates
Ctrl+` | Show formulas | Debug formula issues