## Project Tasks
Task ID | Task Name | Task Type | Parent Task ID | WBS Code | Duration (Days) | Start Date | End Date | Actual Start | Actual End | % Complete | Task Agility | Dependencies | Dependency Type | Lag/Lead | Criticality Level | Resource Assignment | Resource Load % | Cost Budget | Actual Cost | Status | Milestone | Deliverables | Blocking Tasks | Blocked By | Notes | Impact Score | Risk Score | Health Indicator | Priority Score | Total Float | Free Float | Critical Path | Weighted Progress | Rolled Up Progress | Variance Days | SPI | CPI | Risk Mitigation | Lessons Learned
P001 | Digital Transformation Initiative | Parent |  | 1 | 120 | 2024-01-01 | 2024-06-17 | 2024-01-01 |  | 35% | Sequential |  |  | 0 | Critical | Program Management | 100% | 5000000 | 1750000 | In Progress | No | Complete digital transformation |  |  | Strategic initiative for 2024 | 70 | 30 | Yellow | 54 | 0 | 0 | Yes | 35 | 35 | 0 | 0.8 | 1
P002 | Phase 1: Discovery & Planning | Parent | P001 | 1.1 | 20 | 2024-01-01 | 2024-01-29 | 2024-01-01 | 2024-01-20 | 100% | Sequential |  |  | 0 | High | PM Team | 100% | 500000 | 485000 | Complete | No | Requirements and architecture | P003,P004 |  | Foundation phase completed successfully | 77 | 0 | Green | 46 | 5 | 5 | No | 100 | 100 | 0 | 1 | 0.9 |  | In progress
C001 | Stakeholder Interviews | Child | P002 | 1.1.1 | 5 | 2024-01-02 | 2024-01-09 | 2024-01-02 | 2024-01-06 | 100% | Parallel |  |  | 0 | High | BA Team | 80% | 50000 | 48000 | Complete | No | Interview notes and findings | C003 |  | Excellent insights gathered | 43 | 0 | Green | 25 | 5 | 5 | No | 100 | 100 | 0 | 1 | 0.9 |  | In progress
C002 | Current State Analysis | Child | P002 | 1.1.2 | 5 | 2024-01-02 | 2024-01-09 | 2024-01-02 | 2024-01-06 | 100% | Parallel |  |  | 0 | High | Tech Architects | 100% | 75000 | 72000 | Complete | No | As-is documentation | C003 |  | Technical debt identified | 43 | 0 | Green | 25 | 5 | 5 | No | 100 | 100 | 0 | 1 | 0.9 |  | In progress
C003 | Future State Design | Child | P002 | 1.1.3 | 7 | 2024-01-07 | 2024-01-17 | 2024-01-07 | 2024-01-13 | 100% | Sequential | C001,C002 | FS | 0 | Critical | Solution Architects | 100% | 100000 | 98000 | Complete | No | To-be architecture | C004 | C001,C002 | Microservices architecture approved | 86 | 0 | Green | 51 | 0 | 0 | Yes | 100 | 100 | 0 | 1 | 0.9 |  | In progress
P003 | Phase 2: Infrastructure Setup | Parent | P001 | 1.2 | 30 | 2024-01-21 | 2024-03-04 | 2024-01-21 |  | 65% | Parallel | P002 | FS | 0 | High | Infrastructure Team | 100% | 1500000 | 975000 | In Progress | No | Cloud infrastructure ready | P004 | P002 | AWS multi-region setup | 66 | 12 | Yellow | 44 | 5 | 5 | No | 65 | 65 | 0 | 1 | 0.9
C005 | Cloud Account Setup | Child | P003 | 1.2.1 | 3 | 2024-01-21 | 2024-01-25 | 2024-01-21 | 2024-01-23 | 100% | Sequential | P002 | FS | 0 | High | Cloud Team | 50% | 10000 | 9500 | Complete | No | AWS accounts ready | C006,C007 |  | Multi-account strategy implemented | 65 | 0 | Green | 39 | 5 | 5 | No | 100 | 100 | 0 | 1 | 0.9 |  | In progress
C007 | Security Framework | Child | P003 | 1.2.3 | 10 | 2024-01-24 | 2024-02-07 | 2024-01-24 |  | 70% | Parallel | C005 | FS | 0 | Critical | Security Team | 100% | 200000 | 140000 | In Progress | No | Security policies & tools |  | C005 | GDPR compliance in progress | 38 | 15 | Yellow | 28 | 0 | 0 | Yes | 70 | 70 | 0 | 1 | 0.9
P004 | Phase 3: Development Sprint 1 | Parent | P001 | 1.3 | 40 | 2024-02-20 | 2024-04-16 |  |  | 0% | Parallel | P003 | SS | 10 | Critical | Dev Team Alpha | 100% | 1000000 | 0 | Planning | No | Core modules developed | P005 | P003 | Agile development approach | 78 | 0 | Green | 46 | 0 | 0 | Yes | 0 | 0 | 0 | 0.8 | 1
M001 | Project Kickoff Complete | Milestone | P002 | 1.1.0 | 0 | 2024-01-01 |  | 2024-01-01 | 2024-01-01 | 100% | Sequential |  |  | 0 | High | All Teams | 0% | 0 | 0 | Complete | Yes | Kickoff meeting held |  |  | Successful project launch | 45 | 0 | Green | 27 | 5 | 5 | No | 100 | 100 | 0 | 1 | 1 |  | In progress
M002 | Infrastructure Ready | Milestone | P003 | 1.2.0 | 0 | 2024-02-19 |  |  |  | 0% | Sequential | C007 | FS | 0 | Critical | Infrastructure Team | 0% | 0 | 0 | Not Started | Yes | Infrastructure sign-off | P004 |  | Gate 2 milestone | 82 | 0 | Green | 49 | 0 | 0 | Yes | 0 | 0 | 0 | 0.8 | 1
R001 | Security Vulnerability Assessment | Child | P003 | 1.2.9 | 3 | 2024-02-01 | 2024-02-06 | 2024-02-01 |  | 40% | Parallel | C007 | SS | 3 | Critical | Security Team | 100% | 30000 | 12000 | Delayed | No | Vulnerability report |  |  | Critical vulnerabilities found - remediation in progress | 44 | 30 | Orange | 38 | 0 | 0 | Yes | 40 | 40 | -2 | 0.8 | 1

## Dashboard
PROJECT DASHBOARD
Total Tasks: | 12
Completed: | 6
At Risk: | 0
Total Budget: | $8,465,000
Actual Cost: | $3,589,500
Budget Used: | 42.4%
STATUS SUMMARY
In Progress | 3
Complete | 6
Planning | 1
Not Started | 1
Delayed | 1

## Instructions
WORKING PROJECT MANAGEMENT TEMPLATE
OVERVIEW | This template provides a comprehensive project tracking system with calculated impact and risk scores.
KEY FEATURES:
Impact Score | Automatically calculated based on duration, dependencies, criticality, and other factors
Risk Score | Dynamic assessment based on status, progress, and health indicators
Health Indicator | Visual status using color coding (Green/Yellow/Orange/Red)
Priority Score | Combined impact and risk for prioritization
USING THE TEMPLATE:
1. Data Entry | Enter your project tasks with parent-child relationships
2. Update Progress | Regularly update % Complete and Status fields
3. Monitor Health | Watch the Health Indicator and Risk Score columns
4. Review Dashboard | Check the Dashboard sheet for KPIs
FORMULAS:
Impact Score | Considers duration, dependencies, criticality, blocking tasks, and budget
Risk Score | Based on status, progress delays, and health indicators
Priority | Impact × 0.6 + Risk × 0.4
BEST PRACTICES:
Daily Updates | Update task status and progress daily
Risk Review | Address high-risk items immediately
Dependencies | Keep dependency information current
Resource Load | Monitor resource utilization levels